## Sheet1
Task Name | Start Date | End Date | Duration | Responsible Person | Status
Project Kickoff | 2024-11-01 | 2024-11-01 | 1 day | John Smith | Completed
Cloud Infrastructure Assessment | 2024-11-02 | 2024-11-10 | 8 days | Sarah Brown | In Progress
Cloud Vendor Selection | 2024-11-11 | 2024-11-20 | 9 days | Alice Johnson | Planned
Design Cloud Architecture | 2024-11-21 | 2024-12-05 | 15 days | Kevin Lee | Planned
Set Up Development Environment | 2024-12-06 | 2024-12-10 | 4 days | Lisa White | Planned
Data Migration Strategy | 2024-12-11 | 2024-12-20 | 9 days | David Green | Planned
Implement Security Protocols | 2024-12-21 | 2025-01-10 | 20 days | Maria Garcia | Planned
User Acceptance Testing (UAT) | 2025-01-11 | 2025-01-20 | 9 days | Tim Brown | Planned
Deployment to Production | 2025-01-21 | 2025-01-25 | 4 days | Sarah Brown | Planned
Post-Deployment Review | 2025-01-26 | 2025-01-30 | 4 days | John Smith | Planned
Cloud Performance Monitoring Setup | 2025-02-01 | 2025-02-10 | 9 days | Alice Johnson | Planned
Continuous Integration Implementation | 2025-02-11 | 2025-02-20 | 9 days | Kevin Lee | Planned
Cloud Cost Optimization Analysis | 2025-02-21 | 2025-02-28 | 7 days | Maria Garcia | Planned
Staff Training on Cloud Technologies | 2025-03-01 | 2025-03-15 | 14 days | Tim Brown | Planned
Develop Disaster Recovery Plan | 2025-03-16 | 2025-03-25 | 9 days | David Green | Planned
Integrate Third-Party Services | 2025-03-26 | 2025-04-05 | 10 days | Lisa White | Planned
Optimize Cloud Storage Solutions | 2025-04-06 | 2025-04-15 | 9 days | Sarah Brown | Planned
Develop Monitoring Dashboard | 2025-04-16 | 2025-04-25 | 9 days | Alice Johnson | Planned
Conduct Security Audits | 2025-04-26 | 2025-05-05 | 9 days | Maria Garcia | Planned
User Feedback Collection | 2025-05-06 | 2025-05-15 | 9 days | Tim Brown | Planned
Final Project Report Preparation | 2025-05-16 | 2025-05-20 | 4 days | John Smith | Planned
Project Closure | 2025-05-21 | 2025-05-21 | 1 day | Kevin Lee | Planned
Cloud Migration Evaluation | 2025-05-22 | 2025-05-31 | 9 days | David Green | Planned
Continuous Improvement Initiatives | 2025-06-01 | 2025-06-10 | 9 days | Lisa White | Planned
Review Compliance with Regulations | 2025-06-11 | 2025-06-20 | 9 days | Sarah Brown | Planned
Implement Feedback for Improvements | 2025-06-21 | 2025-06-30 | 9 days | Alice Johnson | Planned
Transition to New Cloud Platform | 2025-07-01 | 2025-07-15 | 14 days | Maria Garcia | Planned
Cloud Service Optimization | 2025-07-16 | 2025-07-25 | 9 days | Tim Brown | Planned