## Project Timeline
Task Name | Start Date | End Date | Responsible Person | Status | Duration
Project Kickoff | 2024-03-05 | 2024-03-05 | Emily Johnson | Completed | 0
Agile Assessment Completion | 2024-03-30 | 2024-03-30 | Liam Brown | Completed | 0
Agile Training Completion | 2024-04-30 | 2024-04-30 | Mia Chen | Completed | 0
Cross-Functional Teams Established | 2024-05-15 | 2024-05-15 | Ava Martinez | Completed | 0
Process Redesign Completion | 2024-06-30 | 2024-06-30 | Noah Smith | Completed | 0
Feedback Mechanism Implementation | 2024-08-15 | 2024-08-15 | Sophia Williams | Completed | 0
Project Closure and Handover | 2024-09-01 | 2024-09-30 | Emily Johnson | Pending | 29
Needs Assessment for Staffing | 2024-02-15 | 2024-02-20 | James Thompson | In Progress | 5
Contractor Selection Process | 2024-03-01 | 2024-03-15 | Emma Garcia | In Progress | 14
Training Development for Managers | 2024-04-01 | 2024-04-15 | Mia Chen | In Progress | 14
Compliance Documentation | 2024-04-15 | 2024-04-30 | John Davis | Pending | 15
Performance Metrics Setup | 2024-05-01 | 2024-05-15 | Noah Smith | Pending | 14
Feedback Collection System Deployment | 2024-06-01 | 2024-06-30 | Ava Martinez | Pending | 29
Supplier Assessment for Contingent Staffing | 2024-06-15 | 2024-07-01 | Liam Brown | Pending | 16
Change Management Review | 2024-07-01 | 2024-07-15 | Sophia Williams | Pending | 14