## Sheet1
Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Kickoff | 2024-10-01 | 2024-10-01 | 1 | Emily Johnson | Completed
Requirement Gathering | 2024-10-02 | 2024-10-10 | 9 | Liam Brown | Completed
Risk Assessment | 2024-10-11 | 2024-10-20 | 10 | Noah Smith | In Progress
Stakeholder Review | 2024-10-21 | 2024-10-23 | 3 | Ava Martinez | Planned
Infrastructure Assessment | 2024-10-24 | 2024-10-30 | 7 | Sophia Williams | Planned
Cybersecurity Framework Design | 2024-11-01 | 2024-11-15 | 15 | Liam Brown | Planned
Implementation Planning | 2024-11-16 | 2024-11-20 | 5 | Emily Johnson | Planned
Vendor Selection | 2024-11-21 | 2024-11-28 | 8 | Noah Smith | Planned
Solution Development | 2024-11-29 | 2024-12-15 | 17 | Ava Martinez | Planned
Testing and Quality Assurance | 2024-12-16 | 2025-01-02 | 18 | Sophia Williams | Planned
User Training | 2025-01-03 | 2025-01-10 | 8 | Liam Brown | Planned
Deployment Preparation | 2025-01-11 | 2025-01-15 | 5 | Emily Johnson | Planned
Final Deployment | 2025-01-16 | 2025-01-20 | 5 | Noah Smith | Planned
Post-Deployment Support | 2025-01-21 | 2025-02-01 | 12 | Ava Martinez | Planned
Feedback Collection | 2025-02-02 | 2025-02-10 | 9 | Sophia Williams | Planned
Performance Monitoring | 2025-02-11 | 2025-02-28 | 18 | Liam Brown | Planned
Incident Response Planning | 2025-03-01 | 2025-03-10 | 10 | Noah Smith | Planned
Policy and Procedure Documentation | 2025-03-11 | 2025-03-20 | 10 | Ava Martinez | Planned
Regulatory Compliance Assessment | 2025-03-21 | 2025-03-30 | 10 | Sophia Williams | Planned
Security Awareness Campaign | 2025-03-31 | 2025-04-10 | 11 | Emily Johnson | Planned
System Optimization | 2025-04-11 | 2025-04-25 | 15 | Liam Brown | Planned
Project Review | 2025-04-26 | 2025-04-30 | 5 | Noah Smith | Planned
Final Report Preparation | 2025-05-01 | 2025-05-05 | 5 | Ava Martinez | Planned
Handover to Operations | 2025-05-06 | 2025-05-10 | 5 | Sophia Williams | Planned
Lessons Learned Workshop | 2025-05-11 | 2025-05-15 | 5 | Emily Johnson | Planned
Project Closure | 2025-05-16 | 2025-05-16 | 1 | Liam Brown | Planned
Continuous Improvement Planning | 2025-05-17 | 2025-05-31 | 15 | Noah Smith | Planned
Audit and Evaluation | 2025-06-01 | 2025-06-10 | 10 | Ava Martinez | Planned
Final Stakeholder Review | 2025-06-11 | 2025-06-15 | 5 | Sophia Williams | Planned