## Sheet1
Task Name | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Kickoff | 2024-10-01 | 2024-10-01 | 1 | Project Manager | Completed
Requirements Gathering | 2024-10-02 | 2024-10-15 | 14 | Business Analyst | In Progress
Infrastructure Assessment | 2024-10-16 | 2024-10-22 | 7 | IT Specialist | Planned
Cloud Vendor Selection | 2024-10-23 | 2024-10-30 | 8 | Procurement Lead | Planned
Data Migration Planning | 2024-11-01 | 2024-11-15 | 15 | Data Engineer | Planned
Security Protocol Development | 2024-11-16 | 2024-11-30 | 15 | Security Analyst | Planned
Cloud Environment Setup | 2024-12-01 | 2024-12-15 | 15 | Cloud Architect | Planned
Application Migration Strategy | 2024-12-16 | 2024-12-31 | 16 | IT Specialist | Planned
Testing and Validation | 2025-01-01 | 2025-01-15 | 15 | QA Engineer | Planned
User Training | 2025-01-16 | 2025-01-20 | 5 | Training Coordinator | Planned
Go-Live Preparation | 2025-01-21 | 2025-01-31 | 11 | Project Manager | Planned
Post-Implementation Review | 2025-02-01 | 2025-02-05 | 5 | Project Manager | Planned
Final Project Closure | 2025-02-06 | 2025-02-06 | 1 | Project Manager | Planned
Feedback Collection | 2025-02-07 | 2025-02-14 | 8 | QA Engineer | Planned
Continuous Improvement Plan Development | 2025-02-15 | 2025-02-28 | 14 | Project Manager | Planned
Infrastructure Monitoring Setup | 2025-03-01 | 2025-03-10 | 10 | IT Specialist | Planned
Compliance Check | 2025-03-11 | 2025-03-20 | 10 | Compliance Officer | Planned
Regular Status Reporting | 2025-03-21 | 2025-03-31 | 11 | Project Manager | Planned
Stakeholder Review Meeting | 2025-04-01 | 2025-04-05 | 5 | Project Manager | Planned
Resource Allocation for Future Phases | 2025-04-06 | 2025-04-10 | 5 | Resource Manager | Planned
Long-term Support and Maintenance Planning | 2025-04-11 | 2025-04-15 | 5 | IT Specialist | Planned
Transition to Operations | 2025-04-16 | 2025-04-30 | 15 | Operations Manager | Planned
Final Report Preparation | 2025-05-01 | 2025-05-05 | 5 | Project Manager | Planned
Final Stakeholder Presentation | 2025-05-06 | 2025-05-10 | 5 | Project Manager | Planned